## Slide 1
Weekly Status Report
PEMCO BIM & Report Migration
Tableau Admin & PROD Support
May 01 , 2026

## Slide 2
BIM & Report Migration Project Status
Tasks/Activities completed this week: Analysis of individual policies that are uncommon in BIM vs EDW for understanding both Earned Premium, Written Premium, and Average Written Premium variances -In Progress Built and executed AWM vs. BIM dimension validation for the Online Accounts Report [Active accounts]. Development of Self-Service Accounts Query for Online Accounts Tableau Report – In Progress. Completed AWM rewrite of Active Accounts query; resolved count gaps flagged last week. Self-Service Accounts query (AWM rewrite) — 4 DateTypes built; Employee/Supervisor dimension validation underway, gaps vs BIM under investigation - In Progress Username/email mismatch investigation ongoing — paused pending CIF indicator resolution DevOps #10686 (#10468) remains blocked — AWM truncation fix scheduled for next week's release; downstream work (SQL finalization → destination table → validation → Tableau build) on hold until resolved Reports published to PROD: Monthly Inforce Household and Policy Unit Counts Report (O0300A-M1C-P01) Monthly Manual Write Off Report (O0242A-M1A-P01) Monthly Write Off Report (O0302A-M1B-P01) Engagement Dashboard Quote to Purchase Online and DIA Monthly_Proxy_Emailed_Detail Monthly_Proxy_Emailer_Dashboard Monthly_Proxy_Received_Detail ISO Quota Determination: A data variance related to the Car Years query was discussed with Carly, and the validation task has been handed over to her to assign a resource. Youthful Driver Premium query Results have been validated, documented, and handed over.
Project Name | PEMCO BIM retirement [Data architecture, reporting, Tableau reports] | Week Ending | May 01, 2026
Overall Project Health |  |  | 
Next Milestone: Completion of Requirements for all reports |  |  | 
Overall
Resources
Schedule
Scope
Key - Risk (R) / Actions(A) / Issues(I) / Decisions (D) : | Owner | Due Date | Status
{R} Pemco – Server , DB & required tools access are still in progress along with developer workstation. This has impact on the current discovery phase progress. Team needs to reassess the discovery phase timeline once all the access are provisioned. | PEMCO | June 13- 2025 | Closed

## Slide 3
Agent Dashboard & Tableau Reports – Task Breakdown & Status :
Sl No. | Catergory | Tasks | Duration | Target Date | Dependecy | Status | Remarks | Owner
 | Tableau DS | All policies from BIM have been successfully matched with AWM. The AWM dataset reflects higher counts overall, and importantly, no in-force policies present in BIM are missing in AWM. | 14-Apr | 14-Apr |  | Done |  | Shashank
1.1 | Tableau DS | AWM CIF_policy_party_detail incomplete data |  |  | https://pemcoim.visualstudio.com/IM%20Kanban/_workitems/edit/10686 | In Progress | full root cause (LOB prefix bug, AWM truncation) | PEMCO/ Tad
1.2 | Tableau DS | Currently there are few missing username[email_ids] finding the issue and trying to fix the issue | 2 - 3 days |  |  | On Hold | Most of the analysis is done . However this task can be completed once #10686 bug confirmed and linked to #10468 | Shashank
1.3 | Tableau DS | ### Step 1 — Finalize SQL output grain | 3 |  | #1,#2 | Blocked |  | Shashank
1.4 | Tableau DS | ### Step 2 — Write to destination table | 2 |  | #3 | Blocked |  | Shashank
1.5 | Tableau DS | ### Step 3 — Run final validation | 2 |  | #4 | Blocked |  | Shashank
1.6 | Tableau DS | ### Step 5 — Connect Tableau | 1 |  | #5 | Blocked |  | Shashank
1.7 | Tableau DS | ### Step 6 — Build calculated fields in Tableau | 1 |  | #6 | Blocked |  | Shashank
1.8 | Tableau DS | ### Step 4 — Schedule the refresh |  |  | #7 | Blocked |  | Shashank
1.9 | Tableau DS | Document on the single data source |  |  | Parallel Task |  |  | Shashank
 |  | Online Accounts Report |  |  |  |  |  | 
2.1 | Tableau Report | Online Accounts Report- completed Active Accounts query (AWM rewrite) | 30-Apr | 30-Apr |  | Done |  | Shashank
2.2 | Tableau Report | Self-Service Accounts query— ; covers 4 DateTypes (Activation, Initiation, Inforce, DriverOnly) | 1 to 2 weeks | 12-Apr |  | In Progress |  | Shashank
2.3 | Tableau Report | SSA (Sub tasks) — working on DriverOnly as there is huge difference | 3 Days | 5-May |  | In Progress | 43% gap[working on ways to fix this gap] | Shashank
1 | Agent Dashboard | Active Agents Table - Validation | 2 days |  |  | Complete |  | Samarth/ Venkatesh
2 | Agent Dashboard | Earned Premium Issues: Solve Pemco_Reporting Issues for $0 Earned Premium; Engineering a solution in EDW for Cancelled Policies | ~ 2 weeks |  |  | In Progress |  | Samarth/ Pemco
3 | Agent Dashboard | EP Subtask #1: Analyse integrating additional term premium information into DWM.fact.premium_effective_date_summary | 2 to 4 days |  |  | On Hold | Data Engineering/ Alternate Solution to be identified | Samarth/ Pemco
4 | Agent Dashboard | EP Subtask #2: Sprint Plan: Estimate dates | 1 day |  |  |  |  | Carly
5 | Agent Dashboard | EP Subtask #3: Model Changes that are proposed | 2 to 4 days |  |  |  |  | Samarth/ Pemco
6 | Agent Dashboard | EP Subtask #4: Engineering | 2 to 4 days |  | WP Subtask: #3 |  |  | Samarth/ Pemco
7 | Agent Dashboard | EP Subtask #5: QA | 2 days |  | WP Subtask: #3, #4 |  |  | Samarth/ Pemco
8 | Agent Dashboard | EP Subtask #6: Deployment | 1 day |  | WP Subtask: #3, #4, #5 |  |  | Samarth/ Pemco
9 | Agent Dashboard | Written Premium Issues - Engineering Solution for duplicate premium in Pemco_Reporting logic (DWM.dim.policy_agent) | ~ 2 weeks |  |  | In Progress |  | Samarth/ Pemco
10 | Agent Dashboard | WP Subtask #1: Sprint Plan: Estimate dates | 1 day |  |  |  |  | Carly
11 | Agent Dashboard | WP Subtask #2: Engineering | 2 to 4 days |  |  |  |  | Samarth/ Pemco
12 | Agent Dashboard | WP Subtask #3: QA | 2 days |  | WP Subtask: #2, |  |  | Samarth/ Pemco
13 | Agent Dashboard | WP Subtask #4: Deployment | 1 day |  | WP Subtask: #2, #3 |  |  | Samarth/ Pemco
14 | Agent Dashboard | Additional Analysis of root cause of Written Premium Variance | Apr 20 to Apr 24 |  |  | In Progress | Issues with dim.policy_agent table. currently making detailed analysis notes/document | Samarth/ Pemco
15 | Agent Dashboard | WP Subtask #1: Generate Policy level granular data to Analyse | 1 day |  |  | Complete | Pulled out the policy list and highlighted policies that are uncommon. | 
16 | Agent Dashboard | WP Subtask #2: Categorize the trasaction types - Look for Patterns | 2 days |  |  | In Progress | Looking into highlighted policies and trying to find explainations on the variance | Samarth/ Pemco
17 | Agent Dashboard | WP Subtask #2: Backtrack sourcing and logic (Document the data lineage) | 2 days |  |  | In Progress | Documentation in progress along with the analysis. | Samarth/ Pemco
18 | Agent Dashboard | Periodic Full Data Load of Tables and Agent Dashboard Refresh | 1.5 to 2 days |  |  |  |  | Samarth

## Slide 4
Tableau Admin & PROD Support :
Tasks/Activities completed this week: Tableau Admin: Set up and configuration of a new utility tableau server on Windows OS 2022 - Completed. Completed weekly Tableau maintenance activities. setup and configuration of a new Test Tableau server Node 1 (2025.1.15) on Windows OS 2022 - In progress – 08 May 2026 Working with Edwin to set up the write‑back extension in his dashboards. PROD Support Delivered production support by diagnosing SQL job failures and coordinating escalations with data engineers and relevant users when required.

## Slide 5
Thank You